## Project Plan
Only access and fill out this sheet when instructed to in your learner guide. Use the template below or use any free project management tool available online.
PROJECT PLAN FOR WEB DESIGNING
TASK # | TASK | DEPENDENCY | OWNER | START DATE | END DATE | STATUS | ACTUAL START DATE | ACTUAL END DATE | NOTES
1 | Initial Planning | 1.1 | Kevin Metro | 2023-12-05 | 2024-10-29 | Completed | 2024-10-29 | 2024-10-30
1.1 | Task Identification | 1.1.2 | Kevin Metro | 2023-12-05 | 2024-10-30 | Completed | 2024-10-30 | 2024-10-30
1.2 | Analyzing the Requirements | 1.1.2 | Kevin Metro | 2023-12-13 | 2024-10-30 | Completed | 2024-10-30 | 2024-10-30
1.3 | Planning of the Initial Design and Flow of the Web | 1.1.2 | Kevin Metro | 2023-12-13 | 2024-10-30 | Completed | 2024-10-30 | 2024-11-01
1.4 | Planning to Create the | 1.3 | Kevin Metro | 2023-01-03 | 2024-11-01 | Completed | 2024-11-05 | 2024-11-05
| Prototype Creation | 1.3.1 | Kevin Metro |  | 2024-11-05 | Completed | 2024-11-08 | 2024-11-08
| Creating a Prototype Using Figma | 1.3.1 | Kevin Metro |  | 2024-11-08 | Completed | 2024-11-08 | 2024-11-08
| Doing the Prototype for the Hot Stone Pizza |  | Kevin Metro |  | 2024-11-09 | Completed | 2024-11-08 | 2024-11-08
2 | Programming | 1.4 | Kevin Metro | 2023-01-16 | 2024-11-11 | Completed | 2024-11-11 | 2024-11-12
2.1 | Coding the HTML for the structure of Web Wix | 1.4.1 | Kevin Metro | 2023-01-16 | 2024-11-12 | Completed | 2024-11-12 | 2024-11-13
2.2 | Coding the CSS for style of Web | 1.4.1 | Kevin Metro | 2023-01-16 | 2024-11-13 | Completed | 2024-11-14 | 2024-11-16
2.3 | Coding the Java Script for the Interaction of Web Wix |  | Kevin Metro | 2023-01-16 | 2024-11-14 | Completed | 2024-11-16 | 2024-11-16
2.4 | Compilation of Programs | 2.1-2.3 | Kevin Metro | 2023-01-30 | 2024-11-16 | Completed | 2023-01-25
2.5 | Adding Design | 2.4 | Kevin Metro | 2023-02-07 | 2024-11-20 | Completed
3 | Testing and Editing |  | Kevin Metro | 2023-02-06 | 2024-11-20 | In Progress
3.1 | Checking for Program Errors | 2.4 | Kevin Metro | 2023-02-06 | 2024-11-23 | Completed
3.2 | Checking for Information Errors | 2.4 | Kevin Metro | 2023-02-06 | 2024-11-23 | Completed
3.3 | Making Necessary Adjustments | 3.3 | Kevin Metro | 2023-02-13 | 2024-11-23 | Completed
4 | Finalizing | 3.3 | Kevin Metro | 2023-02-20 | 2024-11-23 | In Progress